## Sheet1
Task Name | Duration | Start | Finish | Completed By | Week 1 | Week 2 | Week 3
Project Initiation
Group Contract | 1hr | 2023-12-12 | 2023-12-12 | Whole Group
Making Trello Board | 2hr | 2023-12-12 | 2024-01-14 | Whole Group
Assigning Team Roles | 30min | 2023-12-12 | 2023-12-12 | Whole Group
Creating Github Group | 1hr | 2023-12-14 | 2024-01-14 | Whole Group
Sprint 1
Research Rasa Chatbot | 2hr | 2023-12-12 | 2023-12-25 | Whole Group
Aims and Objective of the project | 30min | 2023-12-14 | 2023-12-14 | Whole Group
Designing the chatbot | 3hr | 2023-12-12 | 2024-01-15 | Justyna
Designing the Face Recognition | 3hr | 2023-12-12 | 2024-01-15 | Uswat
Creating the necessary tables | 1hr | 2023-12-15 | 2024-01-07 | Shabbir
Sprint Review | 30min | 2023-12-20 | 2023-12-20 | Shabbir
Sprint 2
Sequence Diagram | 20min | 2024-01-05 | 2024-01-05 | Uswat
Use-Case Diagram | 15min | 2024-01-05 | 2024-01-05 | Uswat
Activity Diagram | 30min | 2024-01-06 | 2024-01-06 | Justyna
Creating PowerPoint Presentation | 30min | 2024-01-04 | 2024-01-04 | Justyna
Agile Project Management | 15min | 2024-01-12 | 2024-01-12 | Shabbir
Methodology/SDLC | 15min | 2024-01-12 | 2024-01-12 | Shabbir
Functional and non-Functional req | 30min | 2024-01-08 | 2024-01-08 | Uswat
Designing the presentation | 1hr | 2024-01-04 | 2024-01-15 | Justyna
Sprint Review | 30min | 2024-01-10 | 2024-01-10 | Justyna
Project Schedule Timeframe | 1hr | 2024-01-03 | 2024-01-15 | Shabbir
Sprint 3
Tdd Testing | 30min | 2024-01-13 | 2024-01-13 | Whole Group
Model Evaluation | 10min | 2024-01-13 | 2024-01-13 | Uswat
Check the design for corectness | 30min | 2024-01-14 | 2024-01-14 | Uswat
Work on quality factors | 45min | 2024-01-13 | 2024-01-13 | Whole Group
Final Checks of the Presentation | 30min | 2024-01-14 | 2024-01-15 | Whole Group
Final Checks for the Programme | 1hr | 2024-01-14 | 2024-01-15 | Whole Group
Check if improvements needed | 1hr | 2024-01-14 | 2024-01-15 | Whole Group
Delegate tasks for Presentation | 20min | 2024-01-14 | 2024-01-15 | Justyna
Conduct presentation meeting | 3hr | 2024-01-14 | 2024-01-14 | Whole Group
Sprint Review | 30min | 2024-01-14 | 2024-01-14 | Uswat
Submit the final work | 10min | 2024-01-15 | 2024-01-15 | Uswat